## Slide 1
Evolution of Cenpower Generation Company
2003
2004
2005
2006
2007
2008
2009
2010
2011
2012
2013
2014
2015
Cenpower Generation Company Limited established by founding shareholders (Samuel Brew-Butler, Michael Wilson, Dr. Jimmy Heymann and Kweku Awotwi)
Initial technical studies, including site selection, preliminary engineering and environmental studies conducted
InfraCo joined the founding shareholders as a project development partner
Detailed engineering studies, social and environmental assessments completed. 200MW PPA executed with ECG and EPC procurement process commenced
AFC acquired a controlling stake in Cenpower, becoming the project lead developer and arranger of financing
January 2015: Ground-breaking ceremony to signify start of project construction
August 2014: EPC Contract signed with Group Five
September 2014: Equity Close
October 2014: Debt/Financing documents signed
23rd December 2014: Financial Close
June 2012: 20 year take-or-pay PPA executed with ECG as off-taker for 325MW contractual capacity.
October 2012: Approval of Government Consent and Support Agreement (GCSA) by Parliament of Ghana
3.a. Key stakeholders and Partners
2016
2017
2018
2019
30th November 2018:
Termination of the EPC Contractor’s Engagement and commencement of Step-In phase. After Termination, Step-In team took over and completed outstanding works over the course of 7 months.
23rd December 2014:
Notice to Proceed issued to Group Five and project construction phase commenced and lasted for 44 months.
10th June 2019:
Achievement of Commercial Operations Date under the PPA